# ClassBridge (EMAI)

Mentor Priority Plan & Strategic Roadmap

____________________________________________________________

Version: 1.0
Date: March 22, 2026
Author: Project Mentor / Strategic Advisor
Audience: Theepan Gnanasabapathy (Founder & Developer)
Next Launch: April 14, 2026 (23 days)
Production: classbridge.ca (live since March 6, 2026)

____________________________________________________________

# Table of Contents

1. Strategic Context

2. Current Position Assessment

3. Tier 0: Ship by April 14 (Non-Negotiable)

4. Tier 1: First Week Post-Launch (April 15-22)

5. Tier 2: Second Week Post-Launch (April 22-30)

6. Tier 3: May — Ecosystem Expansion

7. Tier 4: June — Institutional Readiness

8. What to Explicitly NOT Do

9. Revenue Model & Tier Strategy

10. MCP as Competitive Moat

11. Cost Savings Analysis

12. Phase-2 Cherry-Pick Recommendations

13. Risk-Adjusted Timeline

14. Success Metrics & KPIs

15. The Strategy in One Sentence

____________________________________________________________

# 1. Strategic Context

You have 225+ open issues across two repositories, an April 14 launch in 23 days, and one developer. The class-bridge-phase-2 repository contains 247 commits of significant work (34 new models, 40+ routes, 66+ pages) that was never merged. The temptation is to port everything. This plan provides disciplined prioritization based on three principles:

Principle 1: Ship what users need NOW — streaming study guides and daily briefings drive daily engagement

Principle 2: Control costs FIRST — feature flags before new features; every uncontrolled AI call is money burned

Principle 3: Build the moat SECOND — MCP integration and premium features create defensible competitive advantage

This plan is sequenced so that each tier unlocks the next. Feature flags enable cost control, which funds new features, which drive conversion, which funds growth.

# 2. Current Position Assessment

## 2.1 Strengths

Phase 1 MVP is COMPLETE and live in production at classbridge.ca since March 6

1,068+ issues closed — massive velocity for a solo developer

1,004+ backend tests, 258+ frontend tests — strong quality foundation

Google Classroom integration working — key differentiator

AI study tools operational — study guides, quizzes, flashcards, mind maps

4-role RBAC system mature — Parent, Student, Teacher, Admin

Substantial phase-2 code exists (247 commits) — reference implementations available

MCP implementation 50% complete in phase-2 — first-mover opportunity

## 2.2 Risks

Single developer bottleneck — bus factor of 1

AI API costs uncapped — every user gets unlimited access to expensive features

No feature flags — cannot gate features by tier or roll back safely

Phase-2 never merged — tests failing, codebase diverged, some work may need redo

VASP compliance incomplete — blocks school board adoption (25 issues)

No mobile app in stores — PWA not yet enabled

## 2.3 Key Numbers

| Metric | Value |
| --- | --- |
| Days to April 14 Launch | 23 |
| Open Issues (emai-dev-03) | 225+ |
| Phase 2 Completion | ~55% |
| MCP Completion (phase-2) | ~50% |
| Backend Tests | 1,004+ |
| API Endpoints | 1,600+ |
| Database Models | 54 |

# 3. Tier 0: Ship by April 14 (Non-Negotiable)

These are already in-flight. Finish them — nothing else matters until these land. Total estimated effort: 35-44 hours (~1 week of focused work).

| Priority | Task | Issues | Hours | Why |
| --- | --- | --- | --- | --- |
| 0a | Streaming Study Guide (SSE) | #2120-#2127 | 12-16 | Users see a 30s spinner today. Streaming is the single biggest UX improvement you can ship. |
| 0b | Study Guide Contextual Q&A | #2056-#2063 | 10-14 | Extends chatbot into study context. High engagement signal for parents. |
| 0c | Phase 2A: Daily Briefing + Help My Kid | 3 remaining | 6-8 | The "hook" — this makes parents open the app daily. |
| 0d | Phase 2C: Readiness Assessment | 1 remaining | 4-6 | Completes the parent feedback loop. |

# 4. Tier 1: First Week Post-Launch (April 15-22)

Force multipliers — they don't add features, they make everything else cheaper and safer. Total estimated effort: 22-28 hours.

| Priority | Task | Issues | Hours | ROI |
| --- | --- | --- | --- | --- |
| 1a | Feature Flags (24 guards) | #2132, #2154 | 6-8 | ENABLES EVERYTHING BELOW. Gate AI features by tier = 40-60% API cost reduction. Without this you are burning money on free users. Highest-ROI item on the entire backlog. |
| 1b | AI Grade Prediction | #2175 | 8-10 | Cheap to run (tiny prompt, existing data). Answers the #1 parent question: "Will my child pass?" This is your retention hook. |
| 1c | PWA Offline Mode | #2181 | 8-10 | Zero ongoing cost. Eliminates app store submissions. Parents get "install as app" on phones immediately. |

Why this order: Feature flags first because it gates costs. Grade prediction second because it is low-cost high-retention. PWA third because it gives you mobile for free.

# 5. Tier 2: Second Week Post-Launch (April 22-30)

Value features that drive conversion from free to paid. Total estimated effort: 26-34 hours.

| Priority | Task | Issues | Hours | ROI |
| --- | --- | --- | --- | --- |
| 2a | AI Writing Assistant | #2137, #2178 | 12-16 | PREMIUM TIER ANCHOR. Grammar + essay coaching is rare in EdTech. Gate behind feature flag for paid users only. This is what parents will pay for. |
| 2b | Smart Reminders v2 | #2179 | 10-12 | AI-driven contextual nudges. Reduces support tickets. Increases daily active usage. |
| 2c | MCP Foundation + Auth | #2192 | 4-6 | Unlocks entire MCP ecosystem. Low effort, high strategic value. Ship behind feature flag (teacher/admin only initially). |

# 6. Tier 3: May — Ecosystem Expansion

Total estimated effort: 52-74 hours.

| Priority | Task | Issues | Hours | ROI |
| --- | --- | --- | --- | --- |
| 3a | MCP Study + Tutor Tools | #2193, #2194 | 10-14 | Core MCP value — parents use Claude Desktop to check grades, generate study guides via natural language. |
| 3b | Classroom Import (multi-path) | #2160-#2170 | 12-16 | MARKET EXPANSION. Schools blocking Google Classroom API = ~40% of addressable market you currently cannot serve. |
| 3c | 2FA/TOTP Authentication | #2131, #2176 | 10-12 | Compliance requirement. VASP/DTAP requires it for school board adoption. |
| 3d | BYOK (Bring Your Own Key) | New issue needed | 12-20 | Power users bring their own OpenAI key. Shifts 100% of their AI cost off your platform. |
| 3e | Student Goals | #2140 | 8-12 | Engagement + XP integration. Students set goals, earn XP, parents monitor progress. |

# 7. Tier 4: June — Institutional Readiness

Total estimated effort: 57-72 hours.

| Priority | Task | Issues | Hours | Why |
| --- | --- | --- | --- | --- |
| 4a | DTAP Critical 3 | #2143, #2144, #2147 | 12-16 | GATE TO SCHOOL BOARD REVENUE. OAuth decouple, Privacy/ToS pages, OAuth consent screen. Without these, no YRDSB/TDSB/PDSB approval. |
| 4b | MCP Student Resources + Import | #2195, #2196 | 7-10 | Complete MCP coverage for parent/student AI access. |
| 4c | Railway Deployment | #1878-#1889 | 16-20 | clazzbridge.com mirror for redundancy and Canadian hosting. |
| 4d | Student Portfolio | #2173 | 10-12 | Showcase feature — students curate and display their work. |
| 4e | Discussion Forums | #2135, #2177 | 12-14 | Community engagement for parents and students. |

# 8. What to Explicitly NOT Do

These items are tempting but provide zero or negative ROI relative to the priorities above. Explicitly deprioritize them to avoid distraction.

| Item | Why Skip |
| --- | --- |
| Stripe payments (#2159) | Wallet + Interac e-Transfer is sufficient for Canada. Stripe adds complexity and 2.9% fees. |
| AI Email Agent (#2158) | Phase 5 feature. Cool but nobody asked for it. Build when teachers request it. |
| Moodle/Canvas adapters (#2172) | No current customer demand. Build when a specific school board asks for it. |
| Tutor marketplace (#50) | Phase 4+. Requires critical mass of tutors you do not have yet. |
| Newsletter system | Email digests already exist. Newsletters add confusion to communication channels. |
| Attendance tracking | Needs school board data feeds you do not have access to yet. |
| Architecture refactors (#129-#134) | DDD, domain events, repo pattern — zero user value right now. |
| Alembic migration (#185) | CREATE_ALL + ALTER TABLE works. Migration tooling is a time sink with no user impact. |
| E2E testing frameworks (#80) | Unit + integration tests are sufficient. Playwright/Cypress is a maintenance burden. |
| Dark theme options (#678) | Three themes already exist (Light/Dark/Focus). More options add testing burden. |
| Multi-Google account (#945) | Edge case. Most teachers have one Google account. Build if a school requests it. |

# 9. Revenue Model & Tier Strategy

Feature flags make this trivial to implement — you are literally flipping flags per tier, not building separate codebases. This model is designed to maximize free-to-paid conversion.

| Tier | Price | Features |
| --- | --- | --- |
| Free | $0/month | Basic dashboard, 1 study guide/day (gpt-4o-mini), task reminders, Google Classroom view only |
| Standard | $5/month | All AI features with wallet credits, grade prediction, smart reminders, daily briefings, calendar import |
| Premium | $15/month | AI Writing Assistant, MCP access (Claude Desktop), BYOK option, unlimited AI generation, priority support, PDF export |
| School Board | Custom | DTAP-compliant, SSO/SAML, Canadian data residency, admin console, bulk licensing, SLA |

## 9.1 Conversion Funnel

Free: Parent signs up, sees dashboard, gets 1 study guide/day. Sees "Upgrade for Writing Assistant" prompts.

Free to Standard: Parent hits daily limit or wants grade prediction. $5/month removes friction.

Standard to Premium: Parent discovers Writing Assistant or wants Claude Desktop access. $15/month for power features.

School Board: Admin sees value, initiates DTAP process. Custom pricing per district.

# 10. MCP as Competitive Moat

MCP is not just a feature — it is a strategic moat. Here is why it matters more than any individual feature on the backlog:

Distribution without marketing: Every Claude Desktop user (19M+ MAU) can discover ClassBridge through their AI assistant. No ad spend required.

Zero marginal cost: MCP exposes existing API endpoints. It costs nothing extra to serve an MCP request vs a web request.

Network effects: The more AI assistants support MCP, the more valuable ClassBridge becomes. This compounds over time.

Defensibility: Being first to market with MCP in education creates switching costs. Schools that adopt ClassBridge-via-MCP will not easily switch.

Premium justification: MCP access is the most compelling premium feature you can offer — it turns ClassBridge from a web app into an AI-native platform.

## 10.1 MCP Porting Sequence

Week 2 post-launch: MCP Foundation + Auth (4-6 hrs) — unlocks everything

Week 3: Study Material Tools (6-8 hrs) + Tutor Agent (4-6 hrs) — core value

Week 4: Student Resources (3-4 hrs) + Import Tools (4-6 hrs) — complete coverage

Week 5: Google Classroom Tools (4-6 hrs) + Claude Desktop Guide (2-3 hrs) — user enablement

Week 6: Comprehensive Test Suite (6-8 hrs) — production readiness

# 11. Cost Savings Analysis

## 11.1 Current Cost Problem

Every user currently gets unlimited access to expensive AI features (study guides via GPT-4o, quizzes, flashcards, mind maps). At scale, this is unsustainable. Estimated cost per active user: $2-5/month in OpenAI API calls alone.

## 11.2 Cost Reduction Strategies (by priority)

| Strategy | Savings | Effort | When |
| --- | --- | --- | --- |
| Feature Flags + Tier Gating | 40-60% | 6-8 hrs | Week 1 post-launch |
| BYOK (user provides own key) | 100% for BYOK users | 12-20 hrs | May |
| Content hash dedup | 10-20% | 4-6 hrs | Can add incrementally |
| Model downgrades (gpt-4o-mini for basic) | 30-50% | 2-4 hrs | With feature flags |
| Response caching (same topic/course) | 15-25% | 8-12 hrs | June |
| Rate limiting per tier | 20-30% | Included in flags | Week 1 post-launch |

Combined impact: Feature flags alone reduce costs by 40-60%. Adding BYOK and model downgrades can achieve 70-80% cost reduction for the same feature set.

# 12. Phase-2 Cherry-Pick Recommendations

The class-bridge-phase-2 repo has 247 commits of work. Here is the definitive cherry-pick list ordered by immediate cost savings and user value:

| Rank | Feature | Cost Savings | User Value | Effort | Verdict |
| --- | --- | --- | --- | --- | --- |
| 1 | Feature Flags (24 guards) | ★★★★★ | ★★★ | 6-8 hrs | PORT NOW — foundation for everything |
| 2 | AI Grade Prediction | ★★ | ★★★★★ | 8-10 hrs | PORT NOW — #1 parent question answered |
| 3 | PWA Offline Mode | ★★★★ | ★★★★ | 8-10 hrs | PORT NOW — free mobile distribution |
| 4 | AI Writing Assistant | ★★★★ | ★★★★★ | 12-16 hrs | PORT NEXT — premium tier anchor |
| 5 | Smart Reminders v2 | ★★★ | ★★★★ | 10-12 hrs | PORT NEXT — reduces support load |
| 6 | MCP Foundation | ★★★ | ★★★★★ | 4-6 hrs | PORT NEXT — competitive moat |
| 7 | Classroom Import | ★★★ | ★★★★ | 12-16 hrs | MAY — market expansion |
| 8 | 2FA/TOTP | ★ | ★★★★ | 10-12 hrs | MAY — compliance |
| 9 | BYOK System | ★★★★★ | ★★★★ | 12-20 hrs | MAY — shifts cost to power users |
| 10 | Student Goals | ★ | ★★★★ | 8-12 hrs | MAY — engagement driver |

## 12.1 Integration Strategy

IMPORTANT: Do NOT cherry-pick commits from phase-2. The codebases have diverged too much. Instead, use phase-2 as a reference implementation and write fresh code adapted to emai-dev-03 current architecture. Each feature should be a standalone PR on a feature branch.

# 13. Risk-Adjusted Timeline

| Period | Focus | Hours | Risk Level |
| --- | --- | --- | --- |
| Mar 22 - Apr 14 | Tier 0: Streaming, Q&A, Briefing, Readiness | 35-44 | Medium (tight deadline) |
| Apr 14 | LAUNCH DAY | — | — |
| Apr 15-22 | Tier 1: Feature Flags + Grade Prediction + PWA | 22-28 | Low (self-contained) |
| Apr 22-30 | Tier 2: Writing Assistant + Smart Reminders + MCP Foundation | 26-34 | Medium (AI integration) |
| May 1-15 | Tier 3a: MCP Tools + Classroom Import | 22-30 | Medium (multi-pathway) |
| May 16-31 | Tier 3b: 2FA + BYOK + Student Goals | 30-44 | Medium (auth changes) |
| June 1-15 | Tier 4a: DTAP Critical 3 + MCP completion | 19-26 | Low-Medium |
| June 16-30 | Tier 4b: Railway + Portfolio + Forums | 38-46 | Medium (infra) |
| TOTAL | All Tiers | 192-252 | — |

This timeline assumes 40-50 productive hours per week with AI-assisted development. Buffer: 20% contingency is built into the hour estimates. If any tier slips, the subsequent tiers shift — but Tier 0 is immovable.

# 14. Success Metrics & KPIs

| Metric | Target (April 14) | Target (June 30) |
| --- | --- | --- |
| Registered Users | 50+ | 500+ |
| Daily Active Users | 10+ | 100+ |
| Study Guides Generated/Day | 20+ | 200+ |
| AI API Cost/User/Month | $3-5 (uncapped) | <$1 (with flags) |
| Free to Paid Conversion | N/A (no tiers yet) | 5-10% |
| App Store Availability | No | PWA available |
| MCP Tools Available | 0 | 20+ tools |
| School Board Partnerships | 0 | 1 pilot (DTAP submitted) |

# 15. The Strategy in One Sentence

Ship the launch features → add Feature Flags to control costs → add Grade Prediction + PWA for instant value → add Writing Assistant as premium upsell → build MCP for competitive moat → get DTAP for school boards.

____________________________________________________________

This mentor priority plan was prepared on March 22, 2026, based on comprehensive analysis of both ClassBridge repositories (emai-dev-03 production + emai-class-bridge phase-2), 225+ open GitHub issues, and current market conditions. It is designed to maximize value delivery while controlling costs for a solo developer operation approaching public launch.