# ClassBridge - March 6 Phase 1 Pilot Launch Plan

Generated February 27, 2026  |  classbridge.ca

WARNING  #1 RISK: Google OAuth verification (#589) — requires Google review (3-7+ business days). Submit TODAY.

# Timeline

| Date | Milestone |
| --- | --- |
| Today (Feb 27) | 4 dev days remaining |
| Mar 3 (Mon) | Deploy freeze — no more merges to master |
| Mar 4 (Tue) | Dress rehearsal — full end-to-end walkthrough |
| Mar 5 (Wed) | Final smoke tests, pre-launch backup |
| Mar 6 (Thu) | LAUNCH DAY |

# Summary

| Category | Count | Deadline |
| --- | --- | --- |
| Launch blockers (march-6-pilot) | 7 open | Must close by Mar 2 |
| Launch procedures (checklist items) | ~25 items | Mar 3-6 |
| High-value pre-freeze work | ~9 issues | Best effort Feb 27-Mar 2 |
| Deferred post-launch | ~80+ issues | After pilot |

# 1. Launch Blockers

Must close before March 3 deploy freeze. 7 open issues tagged march-6-pilot.

| Issue | Task | Type | Estimate |
| --- | --- | --- | --- |
| #589 | Submit Google OAuth app for production verification | Process | External — Google review takes days |
| #587 | Record Google OAuth demo video for scope verification | Process | 1-2 hrs |
| #457 | Build and distribute ClassBridge mobile app via EAS Build | Build | 2-4 hrs |
| #460 | Link EAS project and update app.json placeholders | Config | 30 min |
| #461 | Register iOS pilot devices for ad hoc distribution | Config | 1 hr |
| #462 | Update pilot docs with real download links after EAS Build | Docs | 30 min |
| #375 | Device testing on physical iOS + Android devices | Testing | 2-3 hrs |

Critical path: #460 -> #457 -> #461 -> #462 -> #375 (mobile build chain)

OAuth path: #587 -> #589 (demo video then submit for Google review)

# 2. Launch Week Procedures

## Mar 3 — Deploy Freeze

[ ]  Send deploy freeze announcement to all contributors

[ ]  Verify all feature branches stay unmerged

## Mar 4 — Dress Rehearsal

[ ]  Web: Login as Parent, Student, Teacher, Admin — verify dashboards

[ ]  Web: Test messaging, notifications, calendar, AI study tools

[ ]  Mobile: Login as Parent on iOS and Android

[ ]  Mobile: Navigate all tabs (Dashboard, Child Overview, Calendar, Messages, Notifications, Profile)

[ ]  Cross-platform: Verify data syncs between web and mobile

[ ]  Verify all pilot accounts can log in

[ ]  Verify correct parent-child linkages

[ ]  Verify demo data is in place (assignments, messages, notifications)

## Mar 5 — Final Smoke Tests

[ ]  Health check: curl -s https://www.classbridge.ca/health

[ ]  Check logs for errors

[ ]  Verify Cloud SQL is RUNNABLE

[ ]  All pilot accounts still log in

[ ]  Pre-launch backup: ./scripts/backup/manual-backup.sh pre-launch

[ ]  Alert policies active (5xx rate, latency, uptime)

[ ]  Welcome emails drafted and ready

[ ]  Mobile download links ready to share

## Mar 6 — Launch Morning

[ ]  Verify services (health check, web loads, Cloud SQL, no errors)

[ ]  Verify all 4 roles on web + parent on mobile

[ ]  Send welcome emails (parent, teacher, student templates)

[ ]  Share mobile download links with pilot parents

[ ]  Open monitoring dashboards (Cloud Run + Cloud SQL metrics)

[ ]  Designate support contact available

## Mar 6 — Post-Launch Afternoon

[ ]  Confirm all pilot participants received welcome emails

[ ]  Confirm at least one parent logged in via mobile

[ ]  Review Cloud Run metrics — no elevated error rates

[ ]  Review Cloud SQL metrics — no connection issues

[ ]  Check GitHub Issues for reported bugs

[ ]  Send 'launch successful' status update to stakeholders

# 3. High-Value Pre-Freeze Work

Best effort before March 3. Not launch blockers, but improves pilot experience.

| Issue | Task | Impact | Estimate |
| --- | --- | --- | --- |
| #509 | Welcome email on registration | Polish — branded onboarding | 2-3 hrs |
| #510 | Verification acknowledgement email | Polish — post-verify marketing | 2-3 hrs |
| #260 | Inspirational messages in emails | Polish — adds personality | 3-4 hrs |
| #833 | Teacher dashboard enhancement (SVG icons, dynamic counts) | UX — teachers are pilot users | 4-6 hrs |
| #834 | Student engagement (streaks, spaced repetition) | UX — students are pilot users | 4-6 hrs |
| #811 | Replace header back button with unified PageNav | UX consistency | 2-3 hrs |
| #142 | Input validation & field length limits | Security hygiene | 3-4 hrs |
| #73 | Missing database indexes | Performance under load | 1-2 hrs |
| #188 | Replace deprecated dependencies (python-jose, PyPDF2) | Tech debt / security | 2-3 hrs |

# 4. Recommended Action Plan

## Day 1 (Feb 27 — Today)

[ ]  Start #587 (record OAuth demo video) -> submit #589 immediately (Google review needs lead time)

[ ]  Start mobile build chain: #460 -> #457

[ ]  Pick up #73 (DB indexes) — quick win, low risk

## Day 2 (Feb 28)

[ ]  Complete #457 (EAS build) -> #461 (register devices) -> #462 (update docs)

[ ]  #375 — Device testing on physical iOS + Android

[ ]  Pick up #509 + #510 (welcome/verification emails)

## Day 3 (Mar 1)

[ ]  #833 or #834 (teacher or student dashboard polish)

[ ]  #260 (inspirational messages in emails)

[ ]  #142 (input validation) or #188 (deprecated deps)

## Day 4 (Mar 2)

[ ]  Buffer day — fix anything that broke

[ ]  Final PR reviews and merges

[ ]  Prep demo data for dress rehearsal

# 5. Deferred Post-Launch

Do NOT touch before March 6. ~80+ issues deferred to post-pilot.

| Category | Issues | Reason to Defer |
| --- | --- | --- |
| Architecture refactoring | #127, #128, #129, #131, #132, #133, #134 | High risk, zero user impact |
| Phase 1 New Workflows | #546-#552 | Large features, destabilizing |
| DTAP/VASP Compliance | #779-#807 (26 issues) | Phase 2, months of work |
| Flat/non-gradient style | #486, #487, #488, #489 | Cosmetic, low risk to defer |
| Teacher multi-Google | #41, #62 | Not needed for pilot |
| Parent Dashboard Redesign | #710-#719 (epic) | Too large, current dashboard works |
| Railway migration | #769-#774 | Infrastructure change = high risk |
| LMS abstraction/Brightspace | #775-#778 | Phase 2 feature |
| PostgreSQL test CI | #156 | Doesn't affect users |
| Alembic migrations | #185 | Infrastructure, not user-facing |
| HCD Tier 3 | #838, #839 | Grade integration + submissions = Phase 2 |
| Mobile unit tests | #490-#494 | Nice-to-have, not blocking launch |

ClassBridge 2026  |  classbridge.ca  |  Confidential