## Overview
ClassBridge - March 6 Phase 1 Pilot Launch Plan
Generated February 27, 2026
TIMELINE
Date | Milestone
Today (Feb 27) | 4 dev days remaining
Mar 3 (Mon) | Deploy freeze — no more merges to master
Mar 4 (Tue) | Dress rehearsal — full end-to-end walkthrough
Mar 5 (Wed) | Final smoke tests, pre-launch backup
Mar 6 (Thu) | LAUNCH DAY
SUMMARY
Category | Count | Deadline
Launch blockers (march-6-pilot) | 7 open | Must close by Mar 2
Launch procedures (checklist items) | ~25 items | Mar 3-6
High-value pre-freeze work | ~9 issues | Best effort Feb 27-Mar 2
Deferred post-launch | ~80+ issues | After pilot
WARNING: #1 RISK — Google OAuth verification (#589) requires Google review (3-7+ business days). Submit TODAY.

## 1. Blockers
LAUNCH BLOCKERS - Must close before March 3 freeze
Done? | Issue | Task | Type | Estimate | Notes
| #589 | Submit Google OAuth app for production verification | Process | External — Google review takes days
| #587 | Record Google OAuth demo video for scope verification | Process | 1-2 hrs
| #457 | Build and distribute ClassBridge mobile app via EAS Build | Build | 2-4 hrs
| #460 | Link EAS project and update app.json placeholders | Config | 30 min
| #461 | Register iOS pilot devices for ad hoc distribution | Config | 1 hr
| #462 | Update pilot docs with real download links after EAS Build | Docs | 30 min
| #375 | Device testing on physical iOS + Android devices | Testing | 2-3 hrs
Critical Path: | #460 -> #457 -> #461 -> #462 -> #375 (mobile build chain is sequential)
#587 -> #589 (OAuth video then submit — Google review has external lead time)

## 2. Launch Procedures
LAUNCH WEEK PROCEDURES (Mar 3-6)
Mar 3 — Deploy Freeze
Done? | # | Task
| 1 | Send deploy freeze announcement to all contributors
| 2 | Verify all feature branches stay unmerged
Mar 4 — Dress Rehearsal
Done? | # | Task
| 1 | Web: Login as Parent, Student, Teacher, Admin — verify dashboards
| 2 | Web: Test messaging, notifications, calendar, AI study tools
| 3 | Mobile: Login as Parent on iOS and Android
| 4 | Mobile: Navigate all tabs (Dashboard, Child Overview, Calendar, Messages, Notifications, Profile)
| 5 | Cross-platform: Verify data syncs between web and mobile
| 6 | Verify all pilot accounts can log in
| 7 | Verify correct parent-child linkages
| 8 | Verify demo data is in place (assignments, messages, notifications)
Mar 5 — Final Smoke Tests
Done? | # | Task
| 1 | Health check: curl -s https://www.classbridge.ca/health
| 2 | Check logs for errors
| 3 | Verify Cloud SQL is RUNNABLE
| 4 | All pilot accounts still log in
| 5 | Pre-launch backup: ./scripts/backup/manual-backup.sh pre-launch
| 6 | Alert policies active (5xx rate, latency, uptime)
| 7 | Welcome emails drafted and ready
| 8 | Mobile download links ready to share
Mar 6 — Launch Morning
Done? | # | Task
| 1 | Verify services (health check, web loads, Cloud SQL, no errors)
| 2 | Verify all 4 roles on web + parent on mobile
| 3 | Send welcome emails (parent, teacher, student templates)
| 4 | Share mobile download links with pilot parents
| 5 | Open monitoring dashboards (Cloud Run + Cloud SQL metrics)
| 6 | Designate support contact available
Mar 6 — Post-Launch Afternoon
Done? | # | Task
| 1 | Confirm all pilot participants received welcome emails
| 2 | Confirm at least one parent logged in via mobile
| 3 | Review Cloud Run metrics — no elevated error rates
| 4 | Review Cloud SQL metrics — no connection issues
| 5 | Check GitHub Issues for reported bugs
| 6 | Send 'launch successful' status update to stakeholders

## 3. Should-Do Pre-Freeze
HIGH-VALUE WORK - Best effort before Mar 3 freeze
Done? | Issue | Task | Impact | Estimate | Notes
| #509 | Welcome email on registration | Polish — branded onboarding | 2-3 hrs
| #510 | Verification acknowledgement email | Polish — post-verify marketing | 2-3 hrs
| #260 | Inspirational messages in emails | Polish — adds personality | 3-4 hrs
| #833 | Teacher dashboard enhancement (SVG icons, dynamic counts) | UX — teachers are pilot users | 4-6 hrs
| #834 | Student engagement (streaks, spaced repetition) | UX — students are pilot users | 4-6 hrs
| #811 | Replace header back button with unified PageNav | UX consistency | 2-3 hrs
| #142 | Input validation & field length limits | Security hygiene | 3-4 hrs
| #73 | Missing database indexes | Performance under load | 1-2 hrs
| #188 | Replace deprecated dependencies (python-jose, PyPDF2) | Tech debt / security | 2-3 hrs

## 4. Action Plan
RECOMMENDED ACTION PLAN (Feb 27 - Mar 2)
Day 1 (Feb 27 — Today)
| 1 | Start #587 (record OAuth demo video) -> submit #589 immediately (Google review needs lead time)
| 2 | Start mobile build chain: #460 -> #457
| 3 | Pick up #73 (DB indexes) — quick win, low risk
Day 2 (Feb 28)
| 1 | Complete #457 (EAS build) -> #461 (register devices) -> #462 (update docs)
| 2 | #375 — Device testing on physical iOS + Android
| 3 | Pick up #509 + #510 (welcome/verification emails)
Day 3 (Mar 1)
| 1 | #833 or #834 (teacher or student dashboard polish)
| 2 | #260 (inspirational messages in emails)
| 3 | #142 (input validation) or #188 (deprecated deps)
Day 4 (Mar 2)
| 1 | Buffer day — fix anything that broke
| 2 | Final PR reviews and merges
| 3 | Prep demo data for dress rehearsal

## 5. Deferred Post-Launch
DEFERRED - Do NOT touch before March 6
Category | Issues | Reason to Defer
Architecture refactoring | #127, #128, #129, #131, #132, #133, #134 | High risk, zero user impact
Phase 1 New Workflows | #546-#552 | Large features, destabilizing
DTAP/VASP Compliance | #779-#807 (26 issues) | Phase 2, months of work
Flat/non-gradient style | #486, #487, #488, #489 | Cosmetic, low risk to defer
Teacher multi-Google | #41, #62 | Not needed for pilot
Parent Dashboard Redesign | #710-#719 (epic) | Too large, current dashboard works
Railway migration | #769-#774 | Infrastructure change = high risk
LMS abstraction/Brightspace | #775-#778 | Phase 2 feature
PostgreSQL test CI | #156 | Doesn't affect users
Alembic migrations | #185 | Infrastructure, not user-facing
HCD Tier 3 | #838, #839 | Grade integration + submissions = Phase 2
Mobile unit tests | #490-#494 | Nice-to-have, not blocking launch