ClassBridge (EMAI)

Comprehensive Project Status Report

Date: March 22, 2026

Prepared by: Claude Code Analysis

# Table of Contents

1. Executive Summary

2. Overall Project Health

3. GitHub Issues Analysis

4. Phase-by-Phase Status

4.1 Phase 1 (MVP)

4.2 Phase 1.5 (Calendar, Content, Mobile)

4.3 Phase 2 (Advanced Features)

4.4 Phase 3 (Course Planning)

4.5 Phase 4 (Tutor Marketplace)

4.6 Phase 5 (AI Email Agent)

4.7 Mobile App

5. Feature Completion by Section

6. All Incomplete Items

7. Open Issues Breakdown

8. Risk Assessment

9. Recommended Priority Plan

9.1 Tier 1 — Fix Now (Before April 14)

9.2 Tier 2 — Build for Growth (Q2 2026)

9.3 Tier 3 — School Board Readiness

9.4 Tier 4 — Future Phases

10. Conclusion

# 1. Executive Summary

ClassBridge is an AI-powered education platform connecting parents, students, teachers, and administrators. The platform integrates Google Classroom, provides AI study tools (guides, quizzes, flashcards, mind maps), and enables parents to actively support their children's education. As of March 22, 2026, the platform has 1,969 GitHub issues tracked with 1,068+ closed.

The platform soft-launched on March 6, 2026 at classbridge.ca with a waitlist flow. The next planned launch milestone is April 14, 2026. Phase 1 MVP is COMPLETE with comprehensive performance optimization deployed across the full stack.

## Key Highlights

Phase 1 MVP: 100% complete — production at classbridge.ca since March 6

Soft launch: Live at classbridge.ca since March 6, 2026

1,068+ issues closed, 217 open across all phases

Mobile MVP built with Expo SDK 54 (React Native)

AI study tools: Study guides, quizzes, flashcards, mind maps all operational

4-role RBAC system: Parent, Student, Teacher, Admin

Google Classroom integration: On-demand sync working

# 2. Overall Project Health

| Metric | Value |
| --- | --- |
| GitHub Issues — Closed | 945 |
| GitHub Issues — Open | 192 |
| GitHub Issue Close Rate | 83% |
| Requirements Checkboxes — Completed | 491 |
| Requirements Checkboxes — Remaining | 170 |
| Requirements Completion Rate | 74% |
| Requirements Files | 7 (features-part1/2/3, roadmap, dashboards, mobile, technical) |
| Soft Launch Date | March 6, 2026 |
| Next Launch Target | April 14, 2026 |
| Deployment Platform | GCP Cloud Run |
| Production URL | https://www.classbridge.ca |

# 3. GitHub Issues Analysis

## Issue Statistics

| Category | Count | Percentage |
| --- | --- | --- |
| Closed Issues | 945 | 83% |
| Open Issues | 192 | 17% |
| Total Issues | 1,137 | 100% |

## Recent Closed Issues (Last 7 Days)

| # | Title | Date |
| --- | --- | --- |
| 1656 | fix: add session idle timeout and reduce refresh token lifetime | 2026-03-13 |
| 1654 | fix: duplicate teacher entries when same email exists via class and manual link | 2026-03-13 |
| 1648 | fix: Help Chatbot items not clickable and chat state not persisted | 2026-03-12 |
| 1646 | fix: SpeedDial FAB overlaps bottom of content on course material pages | 2026-03-12 |
| 1645 | fix: Study guide content truncated for math-heavy assignments | 2026-03-12 |
| 1640 | fix: Help Chatbot not fullscreen on mobile devices | 2026-03-12 |
| 1639 | UX: Add View Source Files button next to Upload Document | 2026-03-12 |
| 1634 | fix: Edit Class modal missing Teacher and Students fields | 2026-03-12 |
| 1633 | Remove gradient style toggle | 2026-03-12 |
| 1628 | fix: broken images in document tab — relative markdown refs | 2026-03-12 |
| 1626 | MyKidsPage panel headers inconsistent with ParentDashboard | 2026-03-10 |
| 1625 | Upload Material modal doesn't show which child is selected | 2026-03-10 |
| 1622 | fix: MyKidsPage polish — school name, View navigation | 2026-03-10 |
| 1621 | fix: Document download 404 for pre-migration content | 2026-03-10 |
| 1620 | fix: Dashboard quick actions reorganization and additions | 2026-03-10 |
| 1619 | feat: Create Class wizard polish and enrollment follow-ups | 2026-03-10 |
| 1618 | fix: Filter parent Recent Activity to relevant items only | 2026-03-10 |
| 1617 | fix: Collapsible dashboard panels, simplified view | 2026-03-10 |
| 1616 | fix: Upload wizard loses class selection and resets | 2026-03-10 |
| 1615 | fix: Chat FAB icon and Study Guide UI polish iterations | 2026-03-10 |

4.1 Phase 1 — MVP (100% Complete)

# 4. Phase-by-Phase Status

## Phase Overview

| Phase | Description | Status | Completion |
| --- | --- | --- | --- |
| Phase 1 | MVP — Core Platform | Nearly Complete | 99% |
| Phase 1.5 | Calendar, Content, Mobile & School Integration | In Progress | ~90% |
| Phase 2 | Advanced Features, Compliance, Monetization | Partially Started | ~45% |
| Phase 3 | Course Planning & Guidance | Not Started | 0% |
| Phase 4 | Tutor Marketplace | Not Started | 0% |
| Phase 5 | AI Email Agent | Not Started | 0% |
| Mobile | Expo SDK 54 React Native App | MVP Built | 77% |

## 4.1 Phase 1 — MVP (99% Complete)

Phase 1 is essentially complete. The core platform is fully functional with Google Classroom integration, AI study tools, RBAC, messaging, calendar, tasks, file upload, and comprehensive UI polish. Only 1 item remains:

Multi-Google account support for teachers (#945)

Key Phase 1 achievements (257 items completed):

Google Classroom integration (on-demand sync)

AI study tools: study guides, quizzes, flashcards, mind maps with difficulty levels

Parent, Student, Teacher, Admin dashboards with role-based views

Calendar with drag-and-drop, day/week/month views, child filtering

Task system with CRUD, entity linking, reminders, archival

Secure parent-teacher messaging with email notifications

File upload with OCR, multi-file support, security hardening (20MB limit, magic bytes)

Theme system (Light/Dark/Focus modes)

Audit logging with admin UI

JWT auth with refresh tokens, password reset, case-insensitive email login

Loading skeletons, styled confirmation modals, lazy chunk retry

Non-blocking AI generation with background processing

Content moderation (Claude Haiku K-12 safety check)

Print & PDF export for all study material types

Waitlist system for soft launch

## 4.2 Phase 1.5 — Calendar, Content, Mobile & School Integration (~90%)

Most Phase 1.5 items are complete. 3 items remain:

| Item | Issue # | Status | Notes |
| --- | --- | --- | --- |
| Google Calendar push integration | #943 | Not Started | Sync tasks/reminders to Google Calendar |
| School board email integration | #942 | Blocked | Waiting on DTAP approval |
| Central document repository | — | Not Started | Shared document storage |

## 4.3 Phase 2 — Advanced Features (~55% Complete)

Phase 2 is the largest phase with the most remaining work. It covers monetization, compliance, advanced AI features, dashboard redesigns, and platform hardening. Many features are epics with multiple sub-tasks.

| Feature Area | Section | Status | % Done | Open Issues |
| --- | --- | --- | --- | --- |
| Upload Modal Redesign | §6.28 | Near Complete | 91% | #1266-#1273 |
| Mobile Responsiveness | §6.18 | In Progress | 24% | #1641 |
| Multi-Role Support | §6.24 | Partial | 69% | #255 |
| Show/Hide Password Toggle | §6.45 | Not Started | 0% | #420 |
| Lottie Animation Loader | §6.46 | Not Started | 0% | #424 |
| Admin Email Templates | §6.49 | Not Started | 0% | #513 |
| Broadcast History | §6.50 | Not Started | 0% | #514 |
| AI Usage Tracking | §6.54 | Partial | 70% | #1650, #1651 |
| Contextual Notes | §6.55 | Partial | 80% | #1090 |
| Help Chatbot RAG | §6.59 | Not Started | 0% | #1355-#1363 |
| Digital Wallet & Subscriptions | §6.60 | Not Started | 0% | #1384-#1392 |
| Smart Daily Briefing | §6.61 | Not Started | 0% | #1403 |
| Help My Kid | §6.62 | Not Started | 0% | #1407 |
| Dashboard Redesign v2 | §6.65 | Not Started | 0% | #1418-#1419 |
| Learn Your Way | §6.69 | Not Started | 0% | #1436, #1441 |
| Smart Data Import | §6.67 | Not Started | 0% | #1431-#1433 |
| VASP/DTAP Compliance | — | Not Started | 0% | #778-#806 (18 issues) |
| MCP Protocol Integration | — | Not Started | 0% | #903-#912 (7 issues) |
| Teacher Grade Entry | — | Not Started | 0% | #665 |
| Study Material Versioning | — | Not Started | 0% | #884 |
| Premium Accounts | — | Not Started | 0% | #1007 |
| BYOK (User AI API Key) | — | Not Started | 0% | #578 |
| Student Progress Analysis | — | Not Started | 0% | #575 |

## 4.4 Phase 3 — Course Planning & Guidance (0% Complete)

Phase 3 focuses on Ontario curriculum integration and academic planning. Not yet started.

Ontario Curriculum Management — download, parse, serve curriculum data (#571)

School Board Integration — board-specific catalogs, student-board linking (#511, #500)

Course Catalog Model — board-scoped high school course database (#500)

Academic Plan Model — multi-year course plan Grade 9-12 (#501)

Prerequisite & Graduation Requirements Engine — OSSD validation (#502)

AI Course Recommendations — personalized guidance (#503)

Semester Planner UI — per-semester course selection (#504)

Multi-Year Planner UI — visual Grade 9-12 grid (#505)

University Pathway Alignment — post-secondary program mapping (#506)

Course Planning Dashboard Integration (#507)

Course Planning Tests (#508)

Multi-language support

Advanced AI personalization

Admin analytics

## 4.5 Phase 4 — Tutor Marketplace (0% Complete)

Phase 4 introduces a marketplace for private tutors. Not yet started.

Private tutor profiles (availability, rates, subjects)

Parent/student tutor search and discovery

AI tutor matching

Booking workflow

Ratings & reviews

Payment integration

## 4.6 Phase 5 — AI Email Agent (0% Complete)

Phase 5 adds AI-powered email capabilities. Not yet started.

AI email sending

Reply ingestion

AI summaries

Searchable archive

## 4.7 Mobile App (77% Complete)

The mobile MVP is built with Expo SDK 54 / React Native. Core screens (login, parent dashboard, child overview, calendar, messages, notifications, profile) are implemented. Remaining work:

Device testing — physical iOS and Android via Expo Go (#375)

Pilot launch checklist — verify production API connection (#376)

Unit & component testing — 8 test suites with Jest + RNTL (#490-#494)

Pilot success criteria — 7 acceptance tests not yet verified

# 5. Feature Completion by Section

| Section | Feature | Done | Remaining | % Complete | Status |
| --- | --- | --- | --- | --- | --- |
| §6.1 | Google Classroom Integration | 7 | 0 | 100% | Complete |
| §6.2 | AI Study Assistant | 7 | 0 | 100% | Complete |
| §6.3 | Registration & Auth | All | 0 | 100% | Complete |
| §6.4 | Courses & Content | All | 0 | 100% | Complete |
| §6.5 | Analytics | All | 0 | 100% | Complete |
| §6.6 | Communication | All | 0 | 100% | Complete |
| §6.7 | Teacher Features | All | 0 | 100% | Complete |
| §6.8-6.14 | Tasks, Audit, etc. | All | 0 | 100% | Complete |
| §6.15 | Theme System | All | 0 | 100% | Complete |
| §6.16 | Layout Redesign | 3 | 2 | 60% | Partial |
| §6.18 | Mobile Support | 4 | 13 | 24% | In Progress |
| §6.24 | Multi-Role Support | 11 | 5 | 69% | Partial |
| §6.28 | Upload Modal Redesign | 29 | 3 | 91% | Near Complete |
| §6.34 | Course Enrollment | Most | 1 | 99% | Near Complete |
| §6.35 | Teacher Invites | Most | 4 | 80% | Partial |
| §6.42 | Admin Messaging | Most | 1 | 95% | Near Complete |
| §6.45 | Password Toggle | 0 | 5 | 0% | Not Started |
| §6.46 | Lottie Loader | 0 | 5 | 0% | Not Started |
| §6.49 | Email Templates | 0 | 7 | 0% | Not Started |
| §6.50 | Broadcast History | 0 | 7 | 0% | Not Started |
| §6.53 | Waitlist System | All | 0 | 100% | Complete |
| §6.54 | AI Usage Limits | Most | 3 | 85% | Partial |
| §6.55 | Contextual Notes | Most | 3 | 80% | Partial |
| §6.56 | Tutorial Pages | Most | 2 | 90% | Near Complete |
| §6.57-6.58 | Teacher Links, Images | All | 0 | 100% | Complete |
| §6.59 | Help Chatbot RAG | 0 | 17 | 0% | Not Started |
| §6.60 | Digital Wallet | 0 | 16 | 0% | Not Started |
| §6.61 | Daily Briefing | 0 | ~8 | 0% | Not Started |
| §6.62 | Help My Kid | 0 | ~6 | 0% | Not Started |
| §6.65 | Dashboard Redesign v2 | 0 | ~8 | 0% | Not Started |
| §6.67 | Smart Data Import | 0 | ~6 | 0% | Not Started |
| §6.69 | Learn Your Way | 0 | ~10 | 0% | Not Started |
| §6.70-6.91 | Recent Features | Most | ~5 | 90% | Near Complete |

# 6. All Incomplete Items

## 6.1 Bugs & Fixes (Immediate)

| Issue | Description | Effort |
| --- | --- | --- |
| #1653 | Mind map branches overlap on desktop (radial layout) | Small |

## 6.2 Phase 1 Remaining (1 item)

| Item | Issue | Priority |
| --- | --- | --- |
| Multi-Google account support for teachers | #945 | Medium |

## 6.3 Phase 1.5 Remaining (3 items)

| Item | Issue | Status |
| --- | --- | --- |
| Google Calendar push integration | #943 | Not Started |
| School board email integration | #942 | Blocked (DTAP) |
| Central document repository | — | Not Started |

## 6.4 Phase 2 — Core Features Not Yet Built

| Feature | Section | Issue(s) | Notes |
| --- | --- | --- | --- |
| Mobile Responsiveness Audit | §6.18 | #1641 | 55+ CSS files missing breakpoints |
| Show/Hide Password Toggle | §6.45 | #420 | 5 locations (Login, Register, Reset, Invite) |
| Lottie Animation Loader | §6.46 | #424 | Replace placeholder with branded animation |
| Admin Email Template Management | §6.49 | #513 | 7 sub-tasks: DB, CRUD, editor, preview |
| Broadcast History Reuse/Resend | §6.50 | #514 | 7 sub-tasks: detail, reuse, resend |
| Help Chatbot RAG Full Build | §6.59 | #1355-#1363 | 17 sub-tasks: YAML, embeddings, RAG, API, widget |
| Help Chatbot Global Search | §6.59.9 | #1630 | Unified SQL search across entities |
| Digital Wallet & Subscriptions | §6.60 | #1384-#1392 | 16 sub-tasks: Stripe, plans, wallet, invoicing |
| Smart Daily Briefing | §6.61 | #1403 | Proactive parent intelligence digest |
| Help My Kid — One-Tap Actions | §6.62 | #1407 | Quick study actions for parents |
| Teacher Dashboard v2 | §6.65.3 | #1418 | Class overview, student alerts, quick actions |
| Admin Dashboard v2 | §6.65.4 | #1419 | Platform health, user activity, quick actions |
| Smart Data Import | §6.67 | #1431-#1433 | Photo capture + email forwarding |
| Learn Your Way | §6.69 | #1436, #1441 | Interest-based personalized learning + paywall |
| AI Token/Cost Tracking | §6.54 | #1650 | Track token counts and cost per generation |
| AI Regenerate Tracking | §6.54 | #1651 | Track original vs regenerated content |
| View All Activities Page | — | #1547 | Unified activity feed |
| Hierarchical Study Guides | — | #1594 | Child guides from parent topics |
| Admin Role Management UI | §6.24 | #255 | Add/remove roles for any user |
| Premium Accounts & Limits | — | #1007 | Subscription tiers with configurable limits |
| BYOK — User AI API Key | — | #578 | Encrypted user-provided OpenAI key |
| GCS File Storage Migration | — | #1643, #572 | Move source files from DB blob to cloud |
| Teacher Grade & Feedback Entry | — | #665 | Per-student per-term grade input |
| Student Progress Analysis | — | #575 | OCR score extraction, AI recommendations |
| Data Privacy & User Rights | — | #787 | Account deletion, data export, consent |

## 6.5 Phase 2 — VASP/DTAP Compliance (18 Issues)

7. Open Issues Breakdown (217 Total)

| Issue | Priority | Description |
| --- | --- | --- |
| #780 | CRITICAL | OpenAI API data residency (US data transfer risk) |
| #779 | CRITICAL | Migrate infrastructure to GCP Canada region |
| #781 | CRITICAL | Update Privacy Policy & ToS for MFIPPA/PIPEDA |
| #782 | CRITICAL | Create Privacy Impact Assessment (PIA) |
| #784 | CRITICAL | Implement MFA/2FA support |
| #785 | HIGH | Implement SSO/SAML for school board integration |
| #787 | HIGH | Data export and right to erasure |
| #789 | HIGH | Dependency vulnerability scanning in CI/CD |
| #790 | HIGH | Annual penetration testing program |
| #791 | HIGH | SOC 2 Type II readiness assessment |
| #792 | HIGH | Obtain cyber liability insurance |
| #793 | HIGH | Create Data Processing Agreement (DPA) template |
| #794 | HIGH | Formal breach notification procedures |
| #795 | MEDIUM | Complete K-12CVAT vendor questionnaire |
| #798 | MEDIUM | Formal data retention and automated purging |
| #799 | MEDIUM | Designate privacy officer |
| #800 | MEDIUM | Enhance audit logging for SOC 2 / VASP |
| #802 | MEDIUM | Identify pilot school board partner |
| #803 | CRITICAL | EPIC: DTAP Compliance — Ontario School Board Approval |
| #804 | MEDIUM | WAF/DDoS protection (Cloud Armor) |
| #806 | MEDIUM | Formal data classification and inventory |

## Note: Many open issues are Phase 2+ epics that were intentionally created as future roadmap items. The 217 open issues do not indicate 217 bugs or blockers.

| Issue | Description |
| --- | --- |
| #903 | EPIC: MCP Protocol Integration — AI-Powered Contextual Learning |
| #906 | Student Academic Context MCP resources and tools |
| #907 | Google Classroom MCP tools |
| #908 | Study Material Generation MCP tools |
| #909 | AI Tutor Agent — contextual study plan generation |
| #910 | Teacher Communication MCP tools |
| #911 | MCP Client — external educational resource discovery |
| #912 | MCP integration tests and Claude Desktop configuration |

# 7. Open Issues Breakdown (192 Total)

| Category | Count | Key Issues |
| --- | --- | --- |
| Active Bugs | ~1 | #1653 |
| Phase 1 Remaining | ~1 | #945 |
| Phase 1.5 | ~3 | #942, #943 |
| Phase 2 Features | ~60 | Subscriptions, dashboards, AI features, data import |
| Phase 2 Compliance (VASP/DTAP) | ~20 | #778-#806 (privacy, security, SOC 2) |
| Phase 2 MCP Integration | ~7 | #903-#912 |
| Phase 2 Monetization | ~8 | #1384-#1392 (Stripe, wallet, invoicing) |
| Phase 2 LMS Integrations | ~3 | #777, #778 (Brightspace/D2L) |
| Phase 3 (Course Planning) | ~12 | #500-#508, #511, #571, #576 |
| Phase 4 (Marketplace) | ~5 | #968 |
| Phase 5 (AI Email) | ~4 | — |
| Mobile App | ~5 | #963, device testing |
| Documentation/Strategy | ~8 | #761, #762, #1429, #1430, #1435 |
| Infrastructure | ~5 | #971, #1643 |
| Upload Wizard | ~7 | #1266-#1273 |
| Other Enhancements | ~45 | Various phase-2 labeled items |

Note: Many open issues are Phase 2+ epics that were intentionally created as future roadmap items. The 192 open issues do not indicate 192 bugs or blockers — the majority are planned features for future phases.

# 8. Risk Assessment

| Risk | Severity | Impact | Mitigation |
| --- | --- | --- | --- |
| Source files stored as DB blobs (#1643) | HIGH | Database performance degradation as user base grows; backup size explosion | Migrate to GCS with signed URLs (#572). Plan for Q2 2026. |
| No monetization infrastructure | HIGH | Cannot generate revenue; 16 sub-tasks for Stripe integration | Prioritize §6.60 Digital Wallet in Q2 2026. |
| 55+ CSS files missing mobile breakpoints (#1641) | HIGH | Poor mobile UX for launch users; classbridge.ca on phones | Systematic CSS audit before April 14 launch. |
| VASP/DTAP compliance not started | HIGH | Cannot partner with Ontario school boards without compliance | Begin with data residency (#779, #780) and privacy docs (#781, #782). |
| OpenAI API data residency (#780) | CRITICAL | Student data processed in US; violates MFIPPA for Ontario boards | Evaluate Azure OpenAI (Canada region) or data processing agreements. |
| No MFA/2FA (#784) | MEDIUM | Security gap for school board requirements | Implement TOTP-based MFA in Phase 2. |
| Session security (#1656) | RESOLVED | Idle timeout and reduced refresh token lifetime implemented | Fixed on 2026-03-13. |
| Help Chatbot not fully built (#1355) | LOW | Basic chatbot exists but RAG/knowledge base not implemented | Phase 2 feature — current basic chatbot is functional. |

# 9. Recommended Priority Plan

## 9.1 Tier 1 — Fix Now (Before April 14, 2026 Launch)

These items directly impact the user experience for the upcoming launch. They should be completed in the next 4 weeks.

| Priority | Task | Issue(s) | Effort | Rationale |
| --- | --- | --- | --- | --- |
| 1 | Fix mind map overlap on desktop | #1653 | Small (1 day) | Visual bug, tagged as bug |
| 2 | Mobile responsiveness audit | #1641 | Large (1-2 weeks) | 55+ CSS files need breakpoints |
| 3 | AI usage token tracking | #1650, #1651 | Medium (3-4 days) | Cost control before scaling |
| 4 | Show/hide password toggle | #420 | Small (1 day) | Basic UX, 5 form fields |
| 5 | Replace tutorial SVG placeholders | #1209 | Small (1 day) | Polish — real screenshots |

## 9.2 Tier 2 — Build for Growth (Q2 2026, Post-Launch)

These features drive user engagement and revenue. Target completion: Q2 2026.

| Priority | Task | Issue(s) | Effort | Rationale |
| --- | --- | --- | --- | --- |
| 8 | Migrate files from DB to GCS | #1643, #572 | Large (1-2 weeks) | Scaling blocker |
| 9 | Digital Wallet & Subscriptions | #1384-#1392 | Epic (4-6 weeks) | Monetization — Stripe |
| 10 | Help Chatbot RAG (full) | #1355-#1363 | Epic (3-4 weeks) | Differentiated support |
| 11 | Teacher & Admin Dashboard v2 | #1418, #1419 | Large (2-3 weeks) | Teacher/admin UX basic |
| 12 | Help My Kid — One-Tap Actions | #1407 | Medium (1-2 weeks) | Parent engagement |
| 13 | Smart Daily Briefing | #1403 | Medium (1-2 weeks) | Proactive parent value |
| 14 | Teacher grade & feedback entry | #665 | Medium (1-2 weeks) | Core teacher workflow |
| 15 | Premium accounts & limits | #1007 | Medium (1 week) | Enable freemium model |

## 9.3 Tier 3 — School Board Readiness (Before Board Partnerships)

Compliance is a prerequisite for any Ontario school board partnership. Estimate 2-3 months of dedicated work. These items are non-negotiable for board approval.

| Priority | Task | Issue(s) | Effort | Rationale |
| --- | --- | --- | --- | --- |
| 16 | GCP Canada region migration | #779 | Large (1 week) | Data residency requirement |
| 17 | OpenAI data residency solution | #780 | Large (2 weeks) | Student data in US is legal risk |
| 18 | Privacy Policy + PIA | #781, #782 | Medium (1-2 weeks) | MFIPPA/PIPEDA compliance |
| 19 | MFA/2FA support | #784 | Large (2 weeks) | Security requirement for boards |
| 20 | SSO/SAML for school boards | #785 | Large (2-3 weeks) | Board IT integration |
| 21 | Data export + right to erasure | #787 | Medium (1 week) | Privacy regulation |
| 22 | Vulnerability scanning in CI/CD | #789 | Medium (3-5 days) | Security baseline |
| 23 | Penetration testing program | #790 | Medium (ongoing) | Annual assessment |
| 24 | SOC 2 readiness assessment | #791 | Large (2-3 months) | Enterprise trust certification |
| 25 | DPA template + breach procedures | #793, #794 | Medium (1-2 weeks) | Legal documentation |

## 9.4 Tier 4 — Future Phases (Q3+ 2026)

These are longer-term roadmap items that should be planned after Tiers 1-3 are substantially complete.

Phase 3: Ontario curriculum integration, academic planning, university pathway alignment (12+ items)

Phase 4: Tutor marketplace — profiles, search, AI matching, booking, ratings (6 items)

Phase 5: AI email agent — sending, ingestion, summaries, archive (4 items)

LMS integrations: Brightspace/D2L, Canvas, Moodle (#967, #777, #778)

MCP Protocol Integration: 7 sub-tasks for AI-powered contextual learning (#903-#912)

ClassBridge has made exceptional progress with a 78% requirements completion rate and 85% GitHub issue close rate. The Phase 1 MVP is complete and live in production at classbridge.ca. Comprehensive performance optimization has been deployed, eliminating N+1 queries, adding 16 database indexes, and improving frontend network resilience.

Multi-language support

Advanced AI personalization

The project has strong momentum — 1,068+ issues closed, a working product in production, comprehensive performance optimization deployed, and a clear multi-phase roadmap. The foundation is solid for scaling to school board partnerships and the April 14 full launch.

# 10. Conclusion

ClassBridge has made exceptional progress with a 74% requirements completion rate and 83% GitHub issue close rate. The Phase 1 MVP is effectively complete at 99%, delivering a fully functional AI-powered education platform with Google Classroom integration, comprehensive study tools, role-based dashboards, and a polished UI.

The platform is live at classbridge.ca since the March 6 soft launch with a waitlist system. The immediate priorities for the April 14 launch are: fixing 1 remaining bug (#1653 mind map overlap), completing the mobile responsiveness audit (55+ CSS files), and implementing AI usage tracking for cost control.

Looking ahead, the two most impactful workstreams are: (1) monetization infrastructure via the Digital Wallet & Subscription system (§6.60), which is entirely unbuilt and required for revenue, and (2) VASP/DTAP compliance (18 issues), which is the gatekeeper for any Ontario school board partnership. Both should be active priorities in Q2 2026.

The project has strong momentum — 945 issues closed, a working product in production, and a clear multi-phase roadmap. The foundation is solid for scaling from soft launch to full market entry.

— End of Report —

# Phase-2 Repository Assessment

A parallel development repository (class-bridge-phase-2) accumulated 247 commits with 34 new database models, 40+ API routes, and 66+ new frontend pages. Analysis reveals that many features were independently re-implemented on emai-dev-03 master, including: XP/gamification, achievement badges, study streaks, AI usage tracking, waitlist, account deletion, data export, resource links, content images, daily/weekly digests, assessment countdown, multilingual summaries, report cards, Pomodoro sessions, study timeline, and wallet/credits.

10 unique features from phase-2 have been identified for porting: 2FA/TOTP authentication, feature flags infrastructure, learning journals, meeting scheduler, discussion forums, peer review, AI writing assistance, AI homework help, wellness check-ins, and student goals. These are tracked under GitHub issues #2130-#2140 with a new "Phase 2F: Phase-2 Port" milestone (due May 1, 2026).

Additionally, 47 open issues were migrated from the emai-class-bridge repo (#2143-#2189) covering DTAP compliance, implemented features needing porting, classroom data import, and test coverage expansion.

## MCP Implementation Status

The phase-2 repo contains a substantial MCP (Model Context Protocol) implementation (~50% complete). 9 new issues created (#2191-#2199) to track porting. ClassBridge would be the first education platform with native MCP support, enabling interaction via Claude Desktop, Cursor, and GitHub Copilot.

## Streaming Study Guide

Streaming Study Guide Generation (SSE): In active development on integrate/streaming-study-guide branch. Implements ChatGPT-like streaming UX for study guide generation using Server-Sent Events. 7 issues tracked (#2120-#2127).